## nextay_project_2024-12-08_06.08
Key | Issue Type | Parent | Summary | Status | Assigned to | Sprint
NP-0 | Epic |  | Planning | Done
NP-0 | Task | NP-0 | Requirement Gathering | Done | All members | NP Sprint 0
Np-0 | Task | NP-0 | Prototyping | Done | All members | NP Sprint 0
NP-0 | Task | NP-0 | Create database structure for this Project | Done | All members | NP Sprint 0
NP-11 | Epic |  | Login & Role Management | Done
NP-1 | Task | NP-11 | Design login page UI. | Done | Alishba Sheikh | NP Sprint 1
NP-15 | Task | NP-11 | Set up user authentication and role-based access control. | Done | Laiba Khan | NP Sprint 2
NP-16 | Task | NP-11 | Test login functionality for different roles. | Done | Laiba Khan | NP Sprint 2
NP-17 | Bug | NP-11 | Incorrect user access to restricted sections | Fixed | Laiba Khan | NP Sprint 2
NP-32 | Task | NP-11 | Implement Login functionality with forget password feature | Done | Laiba Khan | NP Sprint 3
NP-33 | Bug | NP-11 | Detect errors in changing password | Fixed | Laiba Khan | NP Sprint 3
NP-12 | Epic |  | Rooms Management | Done
NP-6 | Task | NP-12 | Design room check-in/check-out UI | Done | Wali Allah | NP Sprint 1
NP-10 | Task | NP-12 | Design Room's management UI | Done | Wali Allah | NP Sprint 1
NP-21 | Task | NP-12 | initial Implementation of room availability and status updates. | Done | Alishba, Fasi tahir | NP Sprint 2
NP-22 | Bug | NP-12 | Unable to check in check out rooms due to some conflicts in API or database system | Fixed | Alishba Sheikh | NP Sprint 2
NP-23 | Task | NP-12 | Add Room Functionality | Done | Wali Allah | NP Sprint 2
NP-24 | Bug | NP-12 | Errors in adding rooms due to server issues | FIxed | Wali Allah | NP Sprint 2
NP-26 | Task | NP-12 | Test Rooms Add functionality by adding multiple rooms | Done | Wali Allah | NP Sprint 2
NP-27 | Task | NP-12 | Test Rooms check in check out functionality by assigning room to customer | Done | Alishba, Fasi tahir | NP Sprint 2
NP-40 | Task | NP-12 | Implement Update / Delete Functionality of Rooms | Done | Wali Allah | NP Sprint 3
NP-41 | Task | NP-12 | Implement check in check out with bill calculation | Done | Wali Allah | NP Sprint 3
NP-42 | Bug | NP-12 | Errors in calculating Bills for the customers | Fixed | Wali Allah | NP Sprint 3
NP-13 | Epic |  | Employee Management | Done
NP-2 | Task | NP-13 | Design employee management UI including Add employee , delete/update Employee | Done | Fasi Tahir | NP Sprint 1
NP-3 | Task | NP-13 | Design attendance tracking UI including mark and view attendance | Done | Fasi Tahir | NP Sprint 1
NP-4 | Task | NP-13 | Design shift management of Employees UI | Done | Fasi Tahir | NP Sprint 1
NP-5 | Task | NP-13 | Design pay and view Salary of Employees | Done | Alishba Sheikh | NP Sprint 1
NP-8 | Task | NP-13 | Design Employee's Promotion UI with view history form | Done | Laiba Khan | NP Sprint 1
NP-19 | Task | NP-13 | Add functionality for adding Employees | Done | Fasi Tahir | NP Sprint 2
NP-20 | Bug | NP-13 | Unable to add employee data in some cases due to API or datatypes | Fixed | Fasi Tahir | NP Sprint 2
NP-25 | Task | NP-13 | test Add employees Functionality by adding multiple employees in database | Done | Fasi Tahir | NP Sprint 2
NP-28 | Task | NP-13 | Implement Delete Functionality of employee | Done | Fasi Tahir | NP Sprint 3
NP-29 | Bug | NP-13 | Unable to delete data in some cases due to database issues | FIxed | Fasi Tahir | NP Sprint 3
NP-34 | Task | NP-13 | Implement Employees Pay salary functionality By finance manager | Done | Alishba Sheikh | NP Sprint 3
NP-35 | Bug | NP-13 | Conflicts in datatypes and error in loading data from database to server | Fixed | Alishba Sheikh | NP Sprint 3
NP-36 | Task | NP-13 | Implement view salary by manager as whole and view salary by Employee | Done | Alishba Sheikh | NP Sprint 3
NP-37 | Bug | NP-13 | Conflict in finding Employee when Employee log in ,and data loading due to server API | Fixed | Alishba Sheikh | NP Sprint 3
NP-38 | Task | NP-13 | Implement Employee Information Updation | Done | Fasi Tahir | NP Sprint 3
NP-39 | Bug | NP-13 | Unable to update Employees information due to wrong data columns and data in database | Fixed | Fasi Tahir | NP Sprint 3
NP-43 | Task | NP-13 | Employee's Shift management | Done | Fasi Tahir | NP Sprint 4
NP-44 | Task | NP-13 | Employee Promotion | Done | Alishba Sheikh | NP Sprint 4
NP-45 | Task | NP-13 | Employee's promotion History | Done | Alishba Sheikh | NP Sprint 4
NP-46 | Task | NP-13 | Employee Attendance mark | Done | Fasi Tahir | NP Sprint 4
NP-47 | Task | NP-13 | View Attendance of Employee | Done | Fasi Tahir | NP Sprint 4
NP-49 | Task | NP-13 | Test the Functionalities of Employees Shift | Done | Fasi Tahir | NP Sprint 4
NP-50 | Task | NP-13 | Bug hunting in Employees management | Done | Laiba Khan | NP Sprint 4
NP-14 | Epic |  | Customer Feedback | Done
NP-7 | Task | NP-14 | Design feedback form UI for customers reviews | Done | Laiba Khan | NP Sprint 1
NP-30 | Task | NP-14 | Implement Feedback functionality of customer and then manager view that feedback | Done | Laiba Khan | NP Sprint 3
NP-31 | Bug | NP-14 | Errors in reading feedback from database due to server or API | FIxed | Laiba Khan | NP Sprint 3
NP-54 | Epic |  | Finanace Management | Done
NP-54 | task | NP-54 | Automatic expense managment | Done | Alishba Sheikh | NP Sprint 4
NP-48 | Task | NP-54 | Profit inspection Graph ( Future addition) | To Do
NP-51 | Task | NP-54 | Stock Management (Future addition) | To Do
NP-55 | Epic |  | Testing System | Done
NP-52 | Task | NP-55 | Test all login and role Functionalities | Done | Laiba Khan | NP Sprint 5
NP-53 | Bug | NP-55 | System Bug hunting | Fixed | Fasi Tahir | NP Sprint 5
NP-55 | Task | NP-55 | Testing Feed back management | Done | Laiba Khan | NP Sprint 5
NP-56 | Task | NP-55 | Testing Employee Management | Done | Fasi Tahir | NP Sprint 5
NP-57 | Task | NP-55 | Testing Room management | Done | Wali Allah | NP Sprint 5
NP-58 | Task | NP-55 | Testing Finanace management | Done | Alishba Sheikh | NP Sprint 5